## Read Me
Supplier Lead Time Tracker
A worked example from Vantelira. Free tool, share it freely.
WHAT THIS FILE DOES
It keeps every supplier's lead time in one place and tells you the date to order by to hit the date you need stock. Enter the lead time, a buffer, and when you need it; the sheet back-calculates your Order-By date and flags what to order now.
THE ONE IDEA
A lead time is not a fact you learn once. It drifts. A packaging lead time moving from 6 weeks to 10 quietly blows up a production window, and nobody notices because the number lived in someone's head. Write it down, date it, and re-check it.
HOW TO USE IT
1. Open the Supplier Lead Times tab. Set the Today's date cell at the top.
2. List your suppliers. In the pink cells, enter the lead time in weeks, a buffer, and the date you last confirmed that lead time (Last Verified).
3. For each line, enter the date you need that item in hand (Need-By Date).
4. Read the Order-By Date and Status columns. ORDER NOW means you are already late; SOON means inside a week; OK means you have room.
5. Re-confirm lead times on a schedule (monthly is a good default) and update Last Verified each time. The oldest Last Verified dates are the ones most likely to bite you.
MAKE IT YOURS: HAND IT TO AN AI AGENT
Paste this into Claude or ChatGPT: "Interview me about my suppliers, one at a time: what each provides, where they ship from, their current lead time, and when I last confirmed it. Then fill in this tracker, set a sensible buffer per supplier, and tell me which lead times look stale enough that I should re-verify them before I plan my next production run."
This is a worked example built on placeholder data. The suppliers, lead times, and dates are illustrative. Replace them with your own.
If you need help, contact us at info@vantelira.com

## Supplier Lead Times
Supplier Lead Time Tracker
Today's date: | 2026-06-09 | <- set this to today. The Order-By date and Status read from it.
Supplier | What They Provide | Location | Lead Time (wks) | Buffer (wks) | Last Verified | Need-By Date | Order-By Date | Days to Order-By | Status | Notes
Glass bottle supplier | 250ml glass bottles | Overseas (import) | 12 | 2 | 2026-05-15 | 2026-09-01 | 2026-05-26 | -14 | ORDER NOW
Pouch supplier | Stand-up pouches | Overseas (import) | 10 | 2 | 2026-05-20 | 2026-08-15 | 2026-05-23 | -17 | ORDER NOW
Label printer | Labels + lidding | Regional | 3 | 1 | 2026-06-01 | 2026-07-15 | 2026-06-17 | 8 | OK
Corrugate supplier | Shipping cartons | Local | 2 | 1 | 2026-06-01 | 2026-07-01 | 2026-06-10 | 1 | SOON
Tomato paste supplier | Tomato paste (drums) | Domestic | 6 | 2 | 2026-04-30 | 2026-08-01 | 2026-06-06 | -3 | ORDER NOW
Olive oil supplier | Bulk olive oil | Import (EU) | 8 | 2 | 2026-05-10 | 2026-08-20 | 2026-06-11 | 2 | SOON
Spice blender | Custom spice blend | Domestic | 5 | 1 | 2026-05-25 | 2026-07-20 | 2026-06-08 | -1 | ORDER NOW
Co-packer | Bottle fill & cap | Regional | 4 | 1 | 2026-06-05 | 2026-07-10 | 2026-06-05 | -4 | ORDER NOW
Freight forwarder | Ocean freight | Global | 5 | 1 | 2026-05-01 | 2026-08-05 | 2026-06-24 | 15 | OK
Pink cells are yours to edit. Order-By, Days to Order-By, and Status calculate themselves.
Re-confirm each lead time on a schedule and update Last Verified. A stale lead time is how a production window gets missed.
Formulas:
Order-By Date = [Need-By Date]-([Lead Time (wks)]+[Buffer (wks)])*7